## Project Planner
Just Capstone
[5 empty] | Period Highlight: | 11 |  |  | Plan Duration | [5 empty] | Actual Start |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEK
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Form group | 1 | 1 | 1 | 2 | 100%
Project description from sponsor | 1 | 2 | 1 | 2 | 100%
Make Gantt Chart | 1 | 11 | 3 | 7 | 100%
Work and understand the mechanistic model | 2 | 2 | 2 | 7 | 100%
Research sampling strategies and NN types/architecture | 2 | 4 | 2 | 8 | 75%
Build more accurate datasets from MM | 4 | 3 | 4 | 6 | 90%
Create skeleton notebook for chosen NN types | 4 | 1 | 4 | 1 | 100%
Integrate data into NN and determine base accuracy | 5 | 1 | 5 | 1 | 100%
Standardize data pre-processing and accuracy metric pipelines, start unit testing | 6 | 4 | 6 | 4 | 50%
Compare model performance on various isotherms | 6 | 3 | 6 | 3 | 100%
Compare model performance on further dataset variants | 6 | 3 | 6 | 5 | 80%
Finalize architecture for three models, demonstrate optimal NN | 8 | 3 | 8 | 4 | 90%
Finalize best practices for interaction between MM and NN | 8 | 3 | 9 | 3 | 90%
Build chromatography visualization tool | 8 | 3 | 9 | 3 | 100%
Finalize documentation and prepare presentation | 10 | 2 | 10 | 2 | 100%